## Client Doc
S.No	Points to be tested	Format on check points & Rax-tech testing Remarks	Table Testing Remarks- Rax-tech	GIPL Factory Cleaner Test Remarks	Final clsoure on Points
1	Power Section	To power On the 6 boards seperately & check for the polaritiy & voltage levels at test points in (BMS PCB/MAIN BOARDPCB/MOTOR PCB/MICRO CONTROLLER PCB)
2	Firmware Download Testing	To download the firmware & confirm the downloading procedure
3	BSP for microcontroller debug port	To provide program to transfer characters or data to check the working of the communication port
4	BSP for Relay ON	To provide program to on/off relay with some ON/OFF control
5	BSP for Battery Charging /Discharging	To provide program to confirm the charging & discharging of the battery
6	BSP for Motor Drivers	To provide program for running the motor with ON/OFF control
7	BSP for Zigbee Testing	To provide program for data transfer check through zigbee
8	BSP for memory card testing	To provide program for data store & transfer to & from memory card
9	BSP for Status LED On	To provide program for LED ON/OFF
10	BSP for input - Proximity sensors	To provide program for checking the ON/OFF status of the sensors
11	BSP for input - Limit swithes	To provide program for checking the ON/OFF status of the Limit switch
12	BSP for safety sensor	To provide program for checking the ON/OFF status of the sensor
13	BSP for Config UART (PC communication port)	To provide program to transfer characters or data to check the working of the communication port
14	BSP for UART 3 & 4	To provide program to transfer characters or data to check the working of the communication port
15	BSP for temperature sensor on BMS	To provide program for accessing the values of the temperature sensors on BMS section
16	BSP for temperature sensors on motor Drivers	To provide program for accessing the values of the temperature sensors on motor drivers
17	BSP for temperature sensors on board	To provide program for accessing the values of the temperature sensors for ON board
18	Other points	To Check the status of Buzzer, 5v Fan, LCD SPI,GPIO points

## POST
POST REQUIREMENT DOCUMENT
T.No	Type	Test Condition	Result Observation	Remarks
1	Power	Main PCB		If power supply is not within limit, then, don't proceed further, check the regulator section
		Give 12V DC (J2: 12V, J4: GND)
		Check for 5V DC voltage across C113	4.90 – 5.10V at the power supply for 5V DC.
		Check for 3.3V DC voltage across C150	3.20 – 3.40V at the power supply for 3.3V DC.
		Micro Controller PCB		Ensure debugger wiring is as given in the Debugger Section
		Check for 3.3V DC voltage between 1st and 5th pins of J205	3.20 – 3.40V at the power supply for 3.3V DC.
		Motor Driver PCB		Ensure the Motor driver card is connected to BMS Card (Vbridge to J302 & J303 and Gnd to J304 & J305) for powering the motor driver section
		Check for 24V DC across C305	23.9 – 24.10V at the power supply for 24V DC.
		Check for 3.3V DC across C306	3.20 – 3.40V at the power supply for 3.3V DC.

		BMS PCB
		Check for 5V DC across C429
		Check for 3.3V DC across C403
		Check DC power across J405 and J411
		Check Solar panel across J413 & J419

2	Processor	Processor card to pluggin in the socket, and debugger to be connected, and run a sample code	Code download/Verify Successfully	If any error seen in the IDE, that should be addressed.
3	Self Test	Connect the Debug COM Port on the controller Pluggin card to PC through TTL to USB Converter.Connect a Loop back cable on the UART2 . Connect a Loop back cable on the UART3. Connect a Loop back cable on the UART4(Config UART). Connect the Motor Driver PCBs A, B, C with the Main card	ON Com Tool observe the display , Welcome to GANGES POST and wait for the string START If received this string Display Debug UART Port is working Fine	If not found this display, either cable connection issue, or UART1 issue to be addressed
4	Self Test		Enter LED TEST. / First LED to ON and display Confirm LED1 ON / On the press of LED1OK or LED1NOK, second LED to ON holding first LED ON condition. Then display Confirm LED2 ON On the press of LED2OK or LED2NOK, third LED to ON holding first and second LED ON condition. Then display Confirm LED3 ON On the press of LED3OK or LED3NOK, fourth LED to ON holding first and second, and third LED ON condition. Then display Confirm LED4 ON On the press of LED4OK or LED4NOK,all four LEDs to hold ON condition. Then display MOVE TO NEXT TEST	If any LED is not blinking, that LED shall be troubleshooted
5	Self Test		Enter LIMIT SWITCH TEST and once that input is sensed from no sense condition, then display LIMIT SWITCH OK. Otherwise display LIMIT SWITCH NOK	If it is not sensed, check the circuit well.
6			Enter PROXIMITY SENSOR TEST and once that input is sensed from no sense condition, then display PROXIMITY SENSOR OK. Otherwise display PROXIMITY SENSOR NOK	If it is not sensed, check the circuit well.
7			Enter SAFETY SENSOR TEST and once that input is sensed from no sense condition, then display SAFETY SENSOR OK. Otherwise display SAFETY SENSOR NOK	If it is not sensed, check the circuit well.
8	Self Test		Send Character "ABCD" through this UART2 port and receive "ABCD". If received successfully, they Display "UART2 is working Fine"	If not found this display, either cable connection issue, or UART2 issue to be addressed
9	Self Test		Send Character "ABCD" through this UART3 port and receive "ABCD". If received successfully, they Display "UART3 is working Fine"	If not found this display, either cable connection issue, or UART3 issue to be addressed
10	Self Test		Send Character "ABCD" through this UART3 port and receive "ABCD". If received successfully, they Display "UART4 is working Fine"	If not found this display, either cable connection issue, or UART4 issue to be addressed
11	Self Test		Enter TEMP SENSOR TEST. Measure the temperature of Motor Control board A, B,C and Display MC-A reads 25Deg , MC-B reads 26Deg, MC-C reads 27Deg	I2C or Cable to be tested
12	Self Test		Enter MOTOR1 ON / display Check / Enter MOTOR1 OFF / display Check
13	Self Test		Enter MOTOR2 ON / display Check / Enter MOTOR2 OFF / display Check
14	Self Test		Enter MOTOR3 ON / display Check / Enter MOTOR3 OFF / display Check
15	Self Test	Flash Memory Test	Enter FLASH MEMORY TEST / On receiving, display Enter any String for READ and WRITE,(string should be entered within # quotes #string#) Once string is received, Save the string in memory and read the memory back and Display the string , if received "FLASH OK" or "FLASH NOK" , continue to next test on display of MOVE TO NEXT TEST	SPI or IC Components to be checked
16	Self Test	SD Card Test	Enter SD CARD TEST / On receiving, display Enter any String for READ and WRITE,(string should be entered within $, for eg) $string$) Once string is received, Save the string in memory and Display the SD CARD WRITE COMPLETE , if received "SD CARD OK" or "SD CARD NOK" , continue to next test on display of MOVE TO NEXT TEST	SPI or IC Components to be checked or chck memory card insertion
17	Self Test	Relay Test	Enter BMS RELAY Test and check for the voltage high on the R404 and R408 resistors after connecting the cable from the Main card.
18	Self Test	BMS Temperature Sensor Test	Enter BMS TEMP TEST and Measure the temperature of BMS and Display BMS TEMP reads- 25Deg
19	Self Test	Battery Charging Test	Check Battery charging voltage by connecting the battery to be charged at J422 (+) & J421()-	If not, check VSYS and Solar connector are connected.
20	Self Test	Buzzer, FAN and GPIO Test	Enter BUZZER-FAN-GPIO TEST and display Confirm Buzzer Pin, check for logic high at Q6 base and if it is logic high, enter BUZZEROK . Otherwise enter BUZZERNOK
			Display Confirm Fan Pin and check for logic high at one pad of R44 and if it is logic high, enter FANOK . Otherwise enter FANNOK
			Display , Confirm GPIO Pins and check for logic high at one pad of C70-C77 and if it is logic high, enter GPIOOK . Otherwise enter GPIONOK / continue to next test on display of MOVE TO NEXT TEST
21	Self Test	Zigbee Test	Pair another Zigbee module with the onboard Zigbee module using XCTU. Send “M11” to the paired module for the MOTOR A to ON and check led1 is on will on and for motor to off Send “M10” check led1 off Above commands are for Motor A	If it is not received, check the device and commands / Zigbee is working or not only is checked.